ACRL Government Relations Committee

SMART Goals for the Legislative Advocate Program

September 17, 2009

DRAFT

Goal 1. Before the end of ALA annual conference 2014 increase the number of Legislative Advocates to at least 435, with representation in each congressional district and all 50 states.

Objectives:

A. Before October 31, 2009 identify key legislative committees dealing with legislation that impacts academic libraries and librarianship in consultation with the ALA Washington Office and ACRL staff.

B. Before December 31,  2009, identify potential advocates who live in the congressional districts (House) and state (Senate) of congressional representatives and Senators who serve on these committees in the 111th Congress by reviewing the ACRL membership roster and working with the appropriate ACRL staff and the ACRL Chapters Legislative Liaisons to identify and solicit advocates. Update this for subsequent Congresses by the end of the first February in each Congress.

C. Increase Legislative Membership by approximately 75 new members per year over a five-year period, prioritizing membership to make sure key congressional districts have representation.

D. Review committee assignments at the beginning of each new congress to determine whether or not the representative / senator has a legislative advocate providing coverage. [by February 1, 2011]

Goal 2.  Continue the availability of the ten $250 travel grants for Legislative Advocates to attend National Library Legislative Day, each year until 2014, emphasizing participation by new legislative advocates.

Objectives:

A. Promote the availability of the travel grants to potential Legislative Advocates via email announcements and listservs. [by when?]

B. Encourage current Legislative Advocates to help spread the word about travel grants to colleagues around the country who might be interested in the library advocacy. (The idea being to “hand pick” colleagues who might be interested.) [by when?]

C. Develop a reporting / assessment measure to evaluate the success of the travel grants in getting legislative advocates actively involved in working with their representatives. [by January 2011]

Goal 3.  Provide statewide training on Legislative Advocacy.

Objectives:

A. Before ALA annual conference 2011, create on-line training session (by enlisting the talent of someone like Stephanie Vance) to be made available to Legislative Chapter Representatives to share with current, new and potential Legislative Advocates.

B. Before ALA Midwinter 2011, expand current Legislative Advocate website content to include a list of names and contact information for all legislative advocates, tips, strategies, FAQ page, recommended reading, etc. to assist new advocates in their role.

C. Gather past presentations and other archived material related to the Legislative Advocacy Program and make available on website in order to share history of advocacy program and agendas. [by when?]

D. Before Midwinter 2011, develop or enhance listserv specifically for the legislative advocates to communicate with each other, sharing ideas and approaches.

E. Each year until 2014, recruit experienced Legislative Advocates to present sessions at state ACRL Chapter meetings and at statewide library organizations to becoming a legislative advocate.

Goal 4.  Make information on who is serving as an advocate more open and easily discernable.

Objectives:

A. Identify experienced Legislative Advocates who might be interested in serving as a mentor to new Legislative Advocates.  [Ongoing]

B. Encourage networking opportunities for current, new and potential legislative advocates via listservs, Legislative Chapter Representatives and other ACRL communications channels as well as at Mid-Winter and Annual meetings. [Ongoing]

Goal 5. Simplify the legislative advocacy application

Objectives:

A. Assign a sub-committee to draft a more streamlined application in order to encourage more applicants to be presented to the Government Relations Committee. [At the 2010 ALA annual conference]

Original Draft: July 31, 2009