Proposed timeline for ACRL 2010 Legislative Agenda (and beyond)

| Date | Responsible | Action |
| --- | --- | --- |
| July-August | Government Relations Vice Chair | Develops timeline for 2010 Legislative Agenda. |
| August-October | Government Relations Chair/Vice Chair | With input from all committee members, determine issues to be included (first round) and committee members volunteer to revise or draft specific sections. Drafts to be completed by October. |
| October | Government Relations Vice Chair | Develops messages to send to other groups to solicit input and develops standard format for gathering information. |
| October 30 | Government Relations Chair | Sends draft agenda to Section Council list. Gives them 6 week deadline to reply as they, in turn, may wish to consult their committees. (Staff liaison Kara Malenfant can help facilitate getting message to Section Council.) |
| November 13 | Government Relations Chair | Sends draft agenda to Copyright and Scholarly Communications Committee Chairs asking for their input (Per committee charges). Gives them 1 month deadline to reply. |
| December 18 | Copyright and Scholarly Communications Committee Chairs | Deadline to provide input to committee. |
| December 18 | Sections Chair | Deadline to provide input to committee. |
| January 17 | Committee | Discusses and debates potential additions at ALA MW meeting in Boston. |
| January 29 | Committee | Submits final versions of segments to Chair for review and editing. |
| February 16 | Government Relations Chair | Submits final draft Legislative Agenda to Board for consideration at their mid March meeting. (Staff liaison Kara Malenfant can help facilitate.) |
| March 19 | ACRL Executive Committee | Reviews and takes action re: adopting agenda at Spring Executive Meeting in Chicago. |
| March 29 | Staff | Publicizes ACRL 2010 Legislative Agenda (including ALA Connect and website). |
| Throughout year | Committee | Checks ALA Legislative Alerts for updates to current legislation. |