# Committee Final Report

Type of report being submitted: Committee Final Report

Date:  6/20/17

Committee Name:  Midwinter Social Committee

Supervising Board Member:  T.J. Szafranski

Chair, Co-Chairs, Assistant Chairs:  Anna Mattonen

Committee members: Kelly Ansley, Melissa Anne Chomintra, Margaret A. Howard

Goals, Objectives, Projects completed (including, but not limited to, any procedures, tip sheets, checklists, etc. created during the reporting year):

Our goal for the Midwinter Social was to organize and host a team trivia night to provide a fun and relaxing environment in which attendees could socialize and network. To accomplish this goal, we hosted a five-round trivia event at the Marriot Marquis complete with a cash bar and light snacks for attendees. We also handed out gift cards as prizes to the top two teams. Anna and Melissa staffed the event with help from our supervising board member, T.J. A recap of the evening is posted on the NMRT Notes blog here: http://www.nmrt.ala.org/notes/?p=696

Other thoughts: I believe trivia has been the main event for a few years now, and while it is a large undertaking to create trivia from scratch, it always seems to give attendees a unique and enjoyable experience. I would recommend trivia for consideration to future committees.

We anticipated 70-80 attendees and only had 40 show up. While this was slightly disappointing, the tables and chairs provided by the venue would not have accommodated many more. To future committees I would suggest making sure your table and chair request is clearly communicated to the host venue before the night of the event. There were also several other socials taking place in the same hallway in which we were located, which suggested scheduling conflicts most likely contribute to lower than anticipated attendance.

Action Items/Issues To Be Resolved – What plans/projects remain which will be carried over or postponed until next year? Have there been any substantial changes in plans requiring a reconsideration or cancellation of projects? Information regarding such will be helpful for future chairs and planners.

There are no further action items for this committee.

Financial Report Section:

| Your budget appropriation (see budget) | a. 1500.00 |
| --- | --- |
| ## Amount which you have spent this year | b. 1250.83 |
| Difference between budgeted amount and amount spent (a-b) | c. 249.17 |

Report submitted by:  Anna Mattonen

Email address:  annamattonen@gmail.com