## Slide 1: Pandemic Project: Undifferentiated Name Authority Records Containing Non-Latin Script Reference(s)
Authority Control Interest Group lightning round and discussion
February 16, 2021
Jessalyn Zoom
Asian and Middle Eastern Division
Acquisitions and Bibliographic Access Directorate
Notes: Hi, my name is Jessalyn Zoom, Chief of the Asian and Middle Easter Division at the Library of Congress. Like many of you, we worked on database cleanup projects during the pandemic. One of them is undifferentiated name authority records containing non-Latin script reference(s). All of you are familiar with the NACO work. This brief presentation will be about the planning and thinking behind the project.

## Slide 2: How Did the Project Come About?
Timeline - Urgency
Project scope – Non-Latin cataloging staff
ILS Office
Key role of Automation Coordinator
Notes: Like many of you, one year ago, all of a sudden, we were sent home due to the Coronavirus outbreak in the U.S.
We couldn’t go back to the Library and had to start full-time telework immediately. How could we quickly jump on meaningful work while staying home? There was a sense of urgency.
There was the ongoing CJK Non-Latin Reference Cleanup Project. But the staff would need training to be familiar with the instruction of the project. Moreover, we needed a project for other language catalogers aside from CJK. Then it came about undifferentiated non-Latin NARs project which complement the CJK reference cleanup project (since undiff NAR is not part of the CJK project,) and the instructions are already there. And all the catalogers in the division could work on the project.
After the project is identified, the next question is, how can we create separate list of undiff. NAR by language. The ILS Office promptly provided us the complete list of the entire undiff NAR in the NACO file. Then our division automation coordinator took on the next crucial step and used MS Access to create the lists by language.

## Slide 3: Preparing the Project
Load LCCNS
  50,000 NARs
  008/32 =b
Query
Voyager tables NARs to bibs
Retrieve
Add up
Group the NAR under
All bib records linked to one NAR
List for Korean language
7 bibs in Korean
3 bibs in English
Notes: Imported into MS Access the LCCNs of 50,816 authority records where 008/32 = b (Personal name in field 100 is used by two or more persons) from lists generated by the ILS Program Office.
Used a query on the Voyager tables that link authority records to bib records.
The query retrieves all bib records linked to one authority record.
It adds up the number of bib records for each language code that occurs in linked BIB_TEXT records.
Assumed the associated language for the name authority was the language with highest bib record count. If the authority record is linked to ten bib records, seven for works in Korean and three for works in English, it’s likely that the NAR is for a Korean name.

## Slide 4: Progress Report
Arabic, CJK, Hebrew, Persian, Russian, Spanish, Yiddish lists
Long term goal
Notes: Now that we have a way to create the list, the project will stay and we will continue to work on it whenever cataloger has an extra time.
That’s all for my presentation. Thank you.