## Slide 1: Report for CA-APIC APIC SFBA Chapter Project EVS Optimization Project 2017
November 3, 2017
Presented by Sue Barnes, RN, CIC, FAPIC

## Slide 2: EVS Optimization Project 2017
Purpose: This has has transitioned from just a toolkit to a project designed to support optimization of local EVS Programs. The project team will identify several local hospitals to participate. The project will involve self-assessment of the EVS program by each participating hospital, a site visit by IP/EVS experts from the project team followed (same day) by a Kick-Off meeting with educational presentations including about the AHE certification program and tools.
Monthly meetings started in June 2017
At the end of the efforts will focus on spreading the EVS Optimization project throughout IP and EVS communities including via CA-APIC, Corporate IP Director Group and other avenues to possible include: IC Today webinar, commentary paper submission to relevant professional journal, presentations at SF and other APIC chapters, submission of oral/poster conference presentations: AHE, APIC, HQI, Hospital Executives.
Notes: designed to support reliable design of environmental cleaning and disinfection in healthcare facilities (including departments where HCWs other than EVS clean the environment) to reduce the risk of HAI (healthcare associated infection). The project team will identify several local hospitals to participate. The project will involve self-assessment of the EVS program by each participating hospital, a site visit by IP/EVS experts from the project team followed (same day) by a Kick-Off meeting with educational presentations including about the AHE certification program and tools. Patti Costello (CEO AHE) is supportive of the project and will be copied on all project meeting notes (pcostello@aha.org)

## Slide 3: Project Team
Project Manager Sue Barnes
Sponsor Contec www.contec.org
Two CA-APIC members on Project Group: Elaine Dekker and May Riley
Project Team: 11 IP members, 6 EVS members, 4 Contec staff, 1 ReadyList staff, 2 HAI HQI members
Patti Costello AHE CEO copied on all meeting notes and invited to present at Kick off meetings (to be scheduled 2018)

## Slide 4: Project Status – Steps Completed
Recruit team members
Develop charter/goals and timeline
Schedule monthly work group meetings
Survey CA-APIC and APIC IP talk to determine if other chapters have done a similar project in order to join forces vs. duplicate efforts (none so far)
Develop outline for project
Establish Drop Box folders for project support materials

## Slide 5: Project Status – Steps Still Pending
Identify test locations (department vs. entire hospitals)
Request test site self assessment
Schedule regular planning meetings
Schedule Education/Kick off meeting in person at test site(s)
Weekly check in phone meetings with test site(s)
Evaluation, adjustment project plan, replicate in two additional sites
Plan for wide sharing such as via conference presentation, webinar, publication.