Undergraduate Certification Timeline

2027-2028 Review Year

Fall Round Dates

Color Coding Key

Dates Relevant to All Programs (Both for Candidacy and for Review)

Dates Relevant to Fall Round Programs Only

Dates Relevant to Fall Round Review Teams

Dates Relevant to Fall Round - All

| Fall Round Date | Responsible Party | Activity |
| --- | --- | --- |
| By January 4, 2027 | AUPHA | AUPHA contacts interested Associate Undergraduate programs on intent to stand for candidacy and Full Undergraduate programs due for renewal on intent to stand for certification. |
| By January 18, 2027 | All Programs | Associate Undergraduate programs notify AUPHA of intent to stand for candidacy. Full Undergraduate programs notify AUPHA of their intent to stand for certification or request an extension, if eligible. |
| January 25, 2027 | AUPHA | AUPHA sends candidacy materials and invoice to programs intending to stand for candidacy. AUPHA sends application, self-study guide, review fee invoice, and eligibility survey to programs intending to stand for certification. |
| By March 19, 2027 | Programs Undergoing Review | Programs slated for certification renewal complete and submit application, eligibility survey, and review fee to AUPHA. |
| By March 31, 2027 | AUPHA | AUPHA notifies programs if they passed eligibility. |
| February 2027 | AUPHA | Pre-certification webinar to review certification process. |
| April 2027 | AUPHA | AUPHA puts out a call for volunteers to serve on review teams. Review teams are formed and vetted for conflicts of interest. |
| June 2027 | AUPHA | AUPHA and UPC leadership approve review teams and chairs. |
| August 2027 | AUPHA | Online reviewer training sessions. After training sessions, AUPHA provides Review Team Chairs with final report template. |
| By September 1, 2027 | Programs Undergoing Review | Programs submit self-study to AUPHA. |
| By September 8, 2027 | AUPHA | AUPHA reviews self-studies and distributes copies to review teams. |
| September 2027 | All | AUPHA works with Programs and Review Teams to schedule and organize virtual review panels. |
| By September 10, 2027 | Review Teams | Review team chairs to make initial contact with program directors. Review teams begin review of self-study. |
| By October 1, 2027 | Review Teams | Review team chairs request additional information from programs with copy to AUPHA. |
| By October 18, 2027 | Programs Undergoing Review | Programs respond with additional information requested. |
| By October 29, 2027 | Review Team Chairs | Review team chairs contact programs (copied to AUPHA,) identifying specific issues for discussion during virtual review panel. |
| By November 4, 2027 | Review Team Chairs | Review team chairs send initial draft of report to review team members. |
| November 8-19, 2027 | All | Virtual review panels are held. |
| December 14, 2027 | Programs Undergoing Review/Review Teams | Programs provide review team and AUPHA with any additional information requested during virtual review panel. Review teams begin final efforts on report. |
| By January 4, 2028 | Review Team Chairs/AUPHA | Review team chairs send draft reports to AUPHA for review. AUPHA forwards draft reports to independent reviewers. |
| By January 6, 2028 | AUPHA | AUPHA reviews draft reports and sends them to the Independent Reviewers to make sure the review team remains within the bounds of the criteria. |
| January 13, 2028 | Independent Reviewers (Review Teams) | Independent Reviewers respond in writing to AUPHA with their findings. (Review teams are required to schedule a meeting between this date and the next deadline listed below to ensure availability in case Independent Reviewers have findings to discuss.) |
| By January 19, 2028 | AUPHA | AUPHA reviews draft reports and forwards them to certifying programs for comment. |
| By January 24, 2028 | AUPHA/Review Team Chairs/ Independent Reviewers | Programs respond in writing to AUPHA, correcting any factual errors and omissions in the report. |
| By January 27, 2028 | Independent Reviewers | Independent Reviewers submit feedback to AUPHA |
| By February 1, 2028 | AUPHA | AUPHA sends draft report to the Undergraduate Program Committee for final review. |
| By February 18, 2028 | UPC/Review Team Chairs | UPC sends reports back to review team/AUPHA with any comments. Review team chairs make any final changes to report. |
| By March 3, 2028 | Review Team Chairs | Review team chairs send final reports to AUPHA with recommended action. |
| March 2028 | AUPHA Board/AUPHA | The AUPHA Board of Directors votes on recommendations. AUPHA staff notifies programs of Board's action after board meeting. |
| By January 29, 2030 | Programs Undergoing Review | If required, programs send interim report to AUPHA on any criteria deemed partially or not met. |
| By February 28, 2030 | AUPHA/UPC | AUPHA and UPC leadership review interim reports and contact programs with results. |