## Timeline
Emergency Plan Creation Timeline
[6 empty] | Week 1 |  |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12
|  |  |  | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
Task | Start Day | Days to Complete | End Day | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Initiation
Name Team Members | 1 | 5 | 5
Kickoff Meeting | 6 | 1 | 6
ICS Training | 6 | 5 | 10
Contact First Responders | 6 | 1 | 6
Research
Research Template Options | 6 | 5 | 10
Choose Template | 11 | 1 | 11
Assess Risks
Complete Risk Prioritization Worksheet | 11 | 5 | 15
Complete Walkthrough Checklist | 11 | 5 | 15
Create List of Issues to be Addressed | 16 | 2 | 17
Write Procedures | 16 | 10 | 25
Create Contact Lists
Create Staff Contact List | 21 | 5 | 25
Create Phone Tree | 26 | 1 | 26
Create External Contact List | 26 | 5 | 30
Complete Communications Plan | 31 | 1 | 31
Collections Issues
Determine Salvage Priorities | 31 | 5 | 35
Identify Collections Hazards | 31 | 5 | 35
Identify Sacred Objects | 31 | 5 | 35
Create Disaster Supply List | 36 | 5 | 40
Write and Distribute Plan
Complete Template Chosen in Research Phase | 41 | 5 | 45
Map Facility (if needed) | 41 | 3 | 43
Submit Plan to Supervisor for Feedback (if needed) | 46 | 5 | 50
Make Changes | 51 | 2 | 52
Copy and Distribute Plan | 53 | 1 | 53
Train Staff
Kickoff Meeting | 56 | 1 | 56
Drills | Schedule randomly, but at least annually
Final Implementation
Schedule Updates | Schedule at least annually
Purchase Supplies | 57 | 2 | 58
Share With First Responders | 60 | 1 | 60

## Phone Tree
Institution Name
Telephone Tree
Date of Last Update
|  |  |  | Name | If this person is unavailable, the first person in the first column intitiates the
| Directions: | Person highlighted in blue calls people highlighted in green. |  | Cell Phone | phone tree
|  | Person highlighted in green calls people highlighted in orange |  | Home Phone
Work Phone
1 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
2 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
3 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
4 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
5 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
6 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone

## Internal Communications Plan
Institution Name
Internal Communications Plan
Date Updated
In case of an emergency, make the following calls
First Calls | Type of Emergency | Call To
| Fire | 911
| Injury | 911
Water
Electrical
Second Calls | Type of Emergency | Call To
Injury
Building Damage
Collections Damage
Computer Damage
Third Calls | All Emergencies | Call To
During Working Hours
After Hours
Adapted from California Preservation Network Disaster Plan Template

## External Communications Plan
Institution Name
External Communications Plan
Date Updated
Staff Roles | Name | Work Phone | Cell Phone
Designated Communications Officer
Emergency Team Leader
Responsible for Updating Web Page
Responsible for Updating Voice Mail
Responsible for Updating Social Media
Action Plan Steps
Communications officer meets with Emergency Team Leader
Situation is assessed and information that can be shared with the public is developed
Communications officer directs staff responsible for updating web page, social media, voicemail to update with appropriate info.
Communications officer meets with press as necessary
Communications officer and Emergency Team Leader meet periodically to discuss what updates should be made.
No staff should talk to press. Instead, refer inquiries to communications officer

## B&W Phone Tree
Institution Name
Telephone Tree
Date of Last Update
|  |  |  | Name | If this person is unavailable, the first person in the first column intitiates the
| Directions: | Person highlighted in black calls people highlighted in gray. |  | Cell Phone | phone tree
|  | Person highlighted in gray calls people with no highlight. |  | Home Phone
Work Phone
1 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
2 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
3 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
4 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
5 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone
6 | Name |  | Name | Name | Name | Name
| Cell Phone |  | Cell Phone | Cell Phone | Cell Phone | Cell Phone
| Home Phone |  | Home Phone | Home Phone | Home Phone | Home Phone
| Work Phone |  | Work Phone | Work Phone | Work Phone | Work Phone