## FY_26 Document
Item | Description | Due for Review | Due Date | Contact(s) | Your Agency Tool(s) | Partner/ Subrecipient 1 | Partner/ Subrecipient 2 | Partner/ Subrecipient 3 | Partner/ Subrecipient 4 | Add partners → →
Application
| Budget Tool |  | 8/31/25 |  | RBS FY_25.xlsx | Subrecipient Application | Subrecipient Application | Subrecipient Application | Subrecipient Application
| Application $ Amount |  |  |  | USCG Allocation
| Carryover $ Amount |  |  |  | USCG BSX-22
| Construction Budget Information (SF-424C) |  |  |  | RBS Program/Partners | Subrecipient Application | Subrecipient Application | Subrecipient Application | Subrecipient Application
| Equipment List |  | 8/31/25 |  | RBS Program/Partners | Subrecipient Application | Subrecipient Application | Subrecipient Application | Subrecipient Application
| Application Narrative |  | 2025-08-31 |  | RBS Program/BLA | Subrecipient Application | Subrecipient Application | Subrecipient Application | Subrecipient Application
Financial Reporting (quarterly)
| Federal Financial Report-SF-425 (Oct. 1 - Dec. 31) |  | 2026-01-30 |  | State/Agency Accounting System
| FederalFinancial Report-SF-425 (Jan. 1 - Mar. 31) |  | 2026-04-30 |  | State/Agency Accounting System
| Federal Financial Report-SF-425 (Apr. 1 - Jun. 30) |  | 2026-07-30 |  | State/Agency Accounting System
| Federal Financial Report-SF-425 (Jul. 1 - Sep. 30) |  | 2026-10-30 |  | State/Agency Accounting System
| Federal Financial Report-SF-425 (FINAL) |  | 2027-01-30 |  | State/Agency Accounting System
Certification of Numbered Vessels |  |  | 2026-01-31 |  | State Cognizant Agency
Report of Certificates of Number Issued to Boats |  |  | 2026-03-01 |  | State Cognizant Agency
Annual Performance Report (narrative) |  |  | 2026-12-31 |  | RBS Application Narrative | Subrecipient Data | Subrecipient Data | Subrecipient Data | Subrecipient Data
| Address Topics in Application Narrative (List) |  |  |  | BARD
| Enforcement |  |  |  | Patrol Logs | Patrol Logs | Patrol Logs | Patrol Logs | Patrol Logs
| Officer Training |  |  |  | Education Coordinator
| Boating Education |  |  |  | Education Coordinator
| Fatalities/Incidents/SAR |  |  |  | BARD
| Subrecipient Support |  |  |  | Subrecipients | Subrecipient Deliverables | Subrecipient Deliverables | Subrecipient Deliverables | Subrecipient Deliverables
| Aids To Navigation |  |  |  | ATON Reporting
| Registered Vessels |  |  |  | Cognizant Agency Reporting
| Asset Enhancements |  |  |  | Equipment & Asset List
| Public Access |  |  |  | Public Access Project Reports | Public Access Project Reports | Public Access Project Reports | Public Access Project Reports | Public Access Project Reports
| Trends |  |  |  | BLA Narrative
| Corrective Action Plan (if applicable) |  |  |  | BLA CAP Tracking
Performance Report Part II (statistical data) |  |  | 2026-12-31
| # of Registered Vessels |  |  |  | Certificate of Numbered Vessels Report
| TBS Staff |  |  |  | Org Charts/Rosters
| Officer Information |  |  |  | Staff Rosters | Staff Rosters | Staff Rosters | Staff Rosters | Staff Rosters
| Officer Training |  |  |  | Training Records | Training Records | Training Records | Training Records | Training Records
| SAR/Patrol Equipment |  |  |  | Equipment/Asset List | Equipment/Asset List | Equipment/Asset List | Equipment/Asset List | Equipment/Asset List
| RBS Activity Hours |  |  |  | Patrol Logs & Summary Document | Patrol Logs | Patrol Logs | Patrol Logs | Patrol Logs
| Citations, Warnings, inspections, SAR, Assists |  |  |  | Patrol Logs & Summary Document | Patrol Logs | Patrol Logs | Patrol Logs | Patrol Logs
| Education & Outreach |  |  |  | Class Rosters | Class Rosters | Class Rosters | Class Rosters | Class Rosters
| Public Service Announcements |  |  |  | Communications Log | Communications Log | Communications Log | Communications Log | Communications Log
| Navigational Aids |  |  |  | ANT Log / Reports and Vendor Reports | Subrecipient Reporting | Subrecipient Reporting | Subrecipient Reporting | Subrecipient Reporting

## LOOK--VT Example
Item | Description | Due Date | VT Contact(s) | Your Agency Tool(s) | VT State Police | Vermont DMV | Vermont Fish & Wildlife | Colchester PD | Grand Isle County Sheriffs Dept
[5 empty] | Al Johnson BLA | Shannon Fassett | Sgt. Jenna Reed | Cpl. Stephen Gutierrez | Sheriff Ray Allen
Application
| Budget Tool | 8/31/25 | Al Johnson (VT BLA) | RBS FY_25.xlsx |  | MOU Application | Subrecipient Application | Subrecipient Application | Subrecipient Application
| Application $ Amount |  | Al Johnson (VT BLA) | USCG Allocation
| Carryover $ Amount |  | Al Johnson (VT BLA) | USCG BSX-22
| Construction Budget Information (SF-424C) |  | Jenna Reed & Mike Wichrowski (VT F&W) | RBS Program/Partners |  |  | Subrecipient Application | Subrecipient Application | Subrecipient Application
| Equipment List | 8/31/25 | Al Johnson (VT BLA) | RBS Program/Partners |  |  | Subrecipient Application | Subrecipient Application | Subrecipient Application
| Application Narrative | 2025-08-31 | Al Johnson (VT BLA) | RBS Program/BLA |  | MOU Application | Subrecipient Application | Subrecipient Application | Subrecipient Application
Financial Reporting (quarterly)
| Federal Financial Report-SF-425 (Oct. 1 - Dec. 31) | 2026-01-30 | Melissa Austin & Sherry Chase (DPS Bus. Office) | State/Agency Accounting System |  | Oct. 1-Dec. 31 Invoice & Deliverables | Oct. 1-Dec. 31 Invoice & Deliverables | Oct. 1-Dec. 31 Invoice & Deliverables | Oct. 1-Dec. 31 Invoice & Deliverables
| Federal Financial Report-SF-425 (Jan. 1 - Mar. 31) | 2026-04-30 |  |  |  | Jan. 1-Mar. 31 Invoice & Deliverables | Jan. 1-Mar. 31 Invoice & Deliverables | Jan. 1-Mar. 31 Invoice & Deliverables | Jan. 1-Mar. 31 Invoice & Deliverables
| Federal Financial Report-SF-425 (Apr. 1 - Jun. 30) | 2026-07-30 |  |  |  | Apr. 1-Jun. 30 Invoice & Deliverables | Apr. 1-Jun. 30 Invoice & Deliverables | Apr. 1-Jun. 30 Invoice & Deliverables | Apr. 1-Jun. 30 Invoice & Deliverables
| Federal Financial Report-SF-425 (Jul. 1 - Sep. 30) | 2026-10-30 |  |  |  | Jul. 1-Sep. 30 Invoice & Deliverables | Jul. 1-Sep. 30 Invoice & Deliverables | Jul. 1-Sep. 30 Invoice & Deliverables | Jul. 1-Sep. 30 Invoice & Deliverables
| Federal Financial Report-SF-425 (FINAL) | 2027-01-30
Certification of Numbered Vessels |  | 2026-01-31 | Leslie Smith (VT DMV) | Cert. of Numbered Vessels Form |  | Certification of Numbered Vessels.PDF
Report of Certificates of Number Issued to Boats |  | 2026-03-01 | Leslie Smith (VT DMV) | CG-3923 |  | CG-3923.PDF
Annual Performance Report (narrative) |  | 2026-12-31 | Al Johnson (VT BLA) | RBS Application Narrative |  | MOU Data | Subrecipient Data | Subrecipient Data | Subrecipient Data
| Address Topics in Application Narrative |  | Jacob Metayer (VSP) | BARD
|  |  | Jacob Metayer (VSP) | Patrol Logs |  |  | Patrol Logs | Patrol Logs | Patrol Logs
|  |  | Jenna Reed (VT F&W) | Education Coordinator |  |  | Quarterly Grant Deliverables
|  |  | Jacob Metayer (VSP) | Training Coordinator |  |  | Quarterly Grant Deliverables | Quarterly Grant Deliverables | Quarterly Grant Deliverables
|  |  | Al Johnson (VT BLA) | Equipment/Asset List |  |  | Equipment/Asset List | Equipment/Asset List | Equipment/Asset List
|  |  | Jenna Reed & Mike Wichrowski (VT F&W) | Public Access Project Reports |  |  | Public Access Project Reports
|  |  | Al Johnson (VT BLA) | Corrective Action Plan Status Update
Performance Report Part II (statistical data) |  | 2026-12-31
| # of Registered Vessels |  | Leslie Smith (VT DMV) | Certificate of Numbered Vessels Report
| RBS Staff |  | Al Johnson (VT BLA) | Org Charts/Rosters |  |  | Org Charts/Rosters | Org Charts/Rosters | Org Charts/Rosters
| Officer Information |  | Jacob Metayer (VSP) | Staff Rosters |  | Staff Rosters | Staff Rosters | Staff Rosters | Staff Rosters
| Officer Training |  | Jacob Metayer (VSP) | Training Records |  | Training Records | Training Records | Training Records | Training Records
| SAR/Patrol Equipment |  | Jacob Metayer (VSP) | Equipment/Asset List |  | Equipment/Asset List | Equipment/Asset List | Equipment/Asset List | Equipment/Asset List
| RBS Activity Hours |  | Jacob Metayer (VSP) and Jenna Reed (VT F&W) | Patrol Logs & Summary Document |  | Patrol Logs | Patrol Logs | Patrol Logs | Patrol Logs
| Citations, Warnings, inspections, SAR, Assists |  | Al Johnson (VT BLA) | Patrol Logs & Summary Document |  | Patrol Logs | Patrol Logs | Patrol Logs | Patrol Logs
| Education & Outreach |  | Jenna Reed (VT F&W) | Class Rosters |  | Class Rosters | Class Rosters | Class Rosters | Class Rosters
| Public Service Announcements |  | Adam Silverman (VSP PIO) | Communications Log |  |  | Communications Log | Communications Log | Communications Log
| Navigational Aids |  | Al Johnson (VT BLA) | ANT Log/Reports and Vendor Reports |  |  |  | Quarterly Grant Deliverables