## How to ...
Active Risk & Opportunity Planning3 How to … Quick Guide
Using the standard model and approach WELCOME TO AROP
Step | Name | Comments
| Purpose/ Background | The purpose of the Active Risk & Opportunity Planning (AROP) process is to ensure that uncertainties in terms of risks and opportunities are being adequately addressed - prior to casting all decisions of the project in stone. Aas such - it is intended to be embedded in the preparation of the Business Case of the project - and naturally to be kept updated during the project phases. Successful implementation of projects is based on prudent and active management - and this naturally includes taking uncertainties into account as we all know the world changes, sometimes in ways we did not plan for.
| Process Improvements | Compared to past risk management - the aim and rationale of the AROP process is to improve risk and opportunity management on a number of parameters as shown below:
| When do use the AROP model | During implementation, it has been discussed that this AROP spreadsheet model is too heavy and "cumbersome" to work with for smaller projects and for simple repetitive projects. Based hereon it has been descided to apply a three level approach depending on a combination of project size and complexity. - Full means full use of this spreadsheet - Light means using a template matching sheet "5 Re-assessment" - No Demands means no formal demands for risk management Business impact is defined by the larger of project outgoings (costs + investments) and assumed 1-year EBIT impact. Newness/complexity is described (i.e. not firmly defined) based on ... new/complex impact can be driven by either one of ... - Project impact spans over multiple Business Areas - Projects directly impacts one or more of the core processes - Project changes master data structure(s) - Project includes use of new technology/platforms Whereas known/simple is projects of a repetitive nature. The project owner may decide to use a higher than required level of AROP implementation.
| Getting Started | This AROP modelling file is built to suit the process steps, and it assumes the following actions … 1) Save the file under your own name in your own directory BEFORE you do any adjustments to this. This way you avoid the next project manager to have to clean up your data. 2) Follow the steps using the description in the yellow text-box (which may be deleted, if you do not feel you'll need it) 3) Enter data in the "grey shaded" areas only ... anything else is automatically calculated and/or transferred 4) Hidden rows/columns are deliberately hideen as these are suporting only The model assumes/enables up to 200 risks or opportunities.
| The Risk and Opportinity Management Process | The generic process is as follows … … followed by a step of continuous update and follow-up from project initiation through implementation and early execution.
| Model Update | It is assumed and recommened that the AROP database in systematically updated and reported upon depending on the project in question. The below updates are seen as "strongly recommended minimum updates": - First AROP model sheets 1 through 5 and the defined reporting is assumed prepared for and embedded in the Business Case for the project and hence ready for the approval of the business case. - The full AROP database to be updated (not everything changed - but considered) for each project gate meeting, including the continuous update of the follow-up sheet. - A full update of the follow-up sheet when the project is closed and operations are "in place". From then on - the risks and oportunities emerging from the project are operational risks and opportunities and should be monitored by line management as such. For each presentation, it is recommended that you save a copy of the AROP file for documentation (i.e. "Project x, gate 2").
The below description will take you stepwise through the AROP tool and process
1 | Identification | It is highly recommended that the project owner or project manager initiates the identification workshop with highlighting and entering the project target to ensure thsi is shared amongst all participants. Risks and opportunities are to be seen vs. this defined target. Do notice that you really need to consider the full business system. Depending on your specific project, you may not have issues emerging from all parts of teh business system, but consider this carefully as you may have elements from each component of the business system - either as risks/opportunities TO the project or (probably more important) as risks/opportunities FROM the project.
1.a | ID Participants | This step is optional, but provides a sheet in which you can "remember" the list of prople who supported the identification of risks. The list is not used elwhere in the AROP tool.
2.1 | Setting Scales | Before you are able to assess the individual risks and opportunities, you need to have the scales upon which you wish to measure these defined. Hence this "pre-step". The scale for probability is pre-defined and need not be addressed. The scale of impact/effect differ between projects, and needs to be specified explicitly. It is recognized based on experience, that this is difficult - but it is important, that everyone have the same understanding of what "high" means, and for some projects - it can be complicated to relate everything to a financial result - hence the need for alternative, but closely aligned scales of/for assessment of impact. A natural starting point could be the project KPI's. However, you need to ensure that the scales are aligned, and hence that "high" is equally severe irrespective of which scale you are using. Ask your business controller to support this part.
2.2 | Assessments | Assessments are based on a combination of likelihood/probability and impact - where the impact scale are as defined as mentioned in the above step 2.1 (as shown below - based on dividing by two) and the generic probability scale is as below…
3 | Prioritization | The prioritization is "given" based on the assessments made, leading to a "heat map" of risks and opportunities like this one
4 | Handling | Handling, i.e. doing something to reduce the risks and enhance the opportunities is done using a combination of efforts - depending on your situation. The generic approaches are as shown in this overview… Please note the last one of each. In the end, when you have "done all you want to do", you end up with an element of risk and opportunity that you "have to" accept as the uncertainty of this project. If you mentally/professionally/ business wise cannot accept this - you need to do more to control your uncertainty.
5 | Re-assessments i.e. revisit the defined uncertainties AFTER the decided handling | Now - based on the fact, that you are doing something to handle the uncertainties of your project - you will need to re-assess these as the impact and/or probabability has changed (assuming your handling has any effect). When doing this - please validate for consistency i.e., if your mitigation is entirely about reducing the impact of a risk - your reassessment of this should not show a reduced probability (and vise versa). Often this step is ignored, whereby we get to implicitly assume, that whatever we do, it is sufficient to ensure an acceptable level of uncertainty - without assessing whether this is actually so or not. The re-assessment ends up being the uncertainty we are prepared to accept for the project.
6 | Follow-Up | During the process of your project and it's subsequent implementation - some risks and opportunities change status, gets passed with- or without materialization etc. You can follow this in the follow-up step, and hence document your risk management, and you may also enter actual incidents (positive or negative), which you had not foreseen (and hence not acted upon), but which actually materialized. This will enhance your learning and improve the AROP of the next project.
The AROP tool further includes a set of reporting sheets to automate the Risk and Opportunity reporting
Reporting | Map | This sheet is a risk reporting for your project, which documents/counts up the ... - Gross risks and opportunities of your project prior to your defined handling - Net risks and opportunities including the impact of your handling actions - Current status including what risks and opportunities have materialized or been resolved without materializing This includes an overall count of risks and opportunites as well. This report is intended to be a supplementary/documetation page of your business case and follow material
| Light Report | This sheet provides a reasonably comprehensive listing based reporting on your portfolio - based on the data of your database (i.e. this model). The reporting is auto-generated, but can be modified to at your discretion. Note: It is highly recommened NOT to alter data, but to use lookup formulas for data collection.
| Report Single uncertainty | This sheet is a complete report on any one risk/opportunity in your database (i.e. this model). This provides your with ready-done reporting on the key uncertainties of your project.
| Overview | This sheet contains as pivot table of all the risks/opportunities with gross and net priority for your documentation. When data are entered, you need to refresh the table (stand in any cell and select "Refresh" from you right hand mouse menu). Note: Based on your data it may be neccessary to adjust the "filter" of the pivot table report.
Good luck - and remember - the risks an opportunities exists, and YOU own them - whether you address them or not
… and … do not forget that "By failing to prepare, you are preparing to fail"Benjamin Franklin

## 1 Identification
Active Risk & Opportunity Planning3 |  |  |  |  | 1 - Risk & Opportunity Identification
<Project Name> |  |  |  |  | Updated … <date>
Project Target (KSF/KPI) |  | Description of project targets (Key Success Factors, Key Performance Indicators)
No. | Grouping | Risk or Opportunity | Risk Name | Issue/Description | Owner | Combi | Gross P | Net P
101 | Group A | R | Name 1 | Issue 1 | Person A | 101 - Name 1
102 | Group B | R | Name 2 | Issue 2 | Person B | 102 - Name 2 | -1 | -1
103 | Group B | R | Name 3 | Issue 3 | Person C | 103 - Name 3 | -4 | -4
104 | Group B | O | Name 4 | Issue 4 | Person A | 104 - Name 4 | 3 | 3
105 | Group B | R | Name 5 | Issue 5 | Person C | 105 - Name 5 | -2 | -2
106 | Group A | O | Name 6 | Issue 6 | Person A | 106 - Name 6 | 4 | 4
107 | [5 empty] | 107 - | 0
108 | [5 empty] | 108 - | 0
109 | [5 empty] | 109 - | 0
110 | [5 empty] | 110 - | 0
111 | [5 empty] | 111 - | 0
112 | [5 empty] | 112 - | 0
113 | [5 empty] | 113 - | 0
114 | [5 empty] | 114 - | 0
115 | [5 empty] | 115 - | 0
116 | [5 empty] | 116 - | 0
117 | [5 empty] | 117 - | 0
118 | [5 empty] | 118 - | 0
119 | [5 empty] | 119 - | 0
120 | [5 empty] | 120 - | 0
121 | [5 empty] | 121 - | 0
122 | [5 empty] | 122 - | 0
123 | [5 empty] | 123 - | 0
124 | [5 empty] | 124 - | 0
125 | [5 empty] | 125 - | 0
126 | [5 empty] | 126 - | 0
127 | [5 empty] | 127 - | 0
128 | [5 empty] | 128 - | 0
129 | [5 empty] | 129 - | 0
130 | [5 empty] | 130 - | 0
131 | [5 empty] | 131 - | 0
132 | [5 empty] | 132 - | 0
133 | [5 empty] | 133 - | 0
134 | [5 empty] | 134 - | 0
135 | [5 empty] | 135 - | 0
136 | [5 empty] | 136 - | 0
137 | [5 empty] | 137 - | 0
138 | [5 empty] | 138 - | 0
139 | [5 empty] | 139 - | 0
140 | [5 empty] | 140 - | 0
141 | [5 empty] | 141 - | 0
142 | [5 empty] | 142 - | 0
143 | [5 empty] | 143 - | 0
144 | [5 empty] | 144 - | 0
145 | [5 empty] | 145 - | 0
146 | [5 empty] | 146 - | 0
147 | [5 empty] | 147 - | 0
148 | [5 empty] | 148 - | 0
149 | [5 empty] | 149 - | 0
150 | [5 empty] | 150 - | 0
151 | [5 empty] | 151 - | 0
152 | [5 empty] | 152 - | 0
153 | [5 empty] | 153 - | 0
154 | [5 empty] | 154 - | 0
155 | [5 empty] | 155 - | 0
156 | [5 empty] | 156 - | 0
157 | [5 empty] | 157 - | 0
158 | [5 empty] | 158 - | 0
159 | [5 empty] | 159 - | 0
160 | [5 empty] | 160 - | 0
161 | [5 empty] | 161 - | 0
162 | [5 empty] | 162 - | 0
163 | [5 empty] | 163 - | 0
164 | [5 empty] | 164 - | 0
165 | [5 empty] | 165 - | 0
166 | [5 empty] | 166 - | 0
167 | [5 empty] | 167 - | 0
168 | [5 empty] | 168 - | 0
169 | [5 empty] | 169 - | 0
170 | [5 empty] | 170 - | 0
171 | [5 empty] | 171 - | 0
172 | [5 empty] | 172 - | 0
173 | [5 empty] | 173 - | 0
174 | [5 empty] | 174 - | 0
175 | [5 empty] | 175 - | 0
176 | [5 empty] | 176 - | 0
177 | [5 empty] | 177 - | 0
178 | [5 empty] | 178 - | 0
179 | [5 empty] | 179 - | 0
180 | [5 empty] | 180 - | 0
181 | [5 empty] | 181 - | 0
182 | [5 empty] | 182 - | 0
183 | [5 empty] | 183 - | 0
184 | [5 empty] | 184 - | 0
185 | [5 empty] | 185 - | 0
186 | [5 empty] | 186 - | 0
187 | [5 empty] | 187 - | 0
188 | [5 empty] | 188 - | 0
189 | [5 empty] | 189 - | 0
190 | [5 empty] | 190 - | 0
191 | [5 empty] | 191 - | 0
192 | [5 empty] | 192 - | 0
193 | [5 empty] | 193 - | 0
194 | [5 empty] | 194 - | 0
195 | [5 empty] | 195 - | 0
196 | [5 empty] | 196 - | 0
197 | [5 empty] | 197 - | 0
198 | [5 empty] | 198 - | 0
199 | [5 empty] | 199 - | 0
200 | [5 empty] | 200 - | 0
201 | [5 empty] | 201 - | 0
202 | [5 empty] | 202 - | 0
203 | [5 empty] | 203 - | 0
204 | [5 empty] | 204 - | 0
205 | [5 empty] | 205 - | 0
206 | [5 empty] | 206 - | 0
207 | [5 empty] | 207 - | 0
208 | [5 empty] | 208 - | 0
209 | [5 empty] | 209 - | 0
210 | [5 empty] | 210 - | 0
211 | [5 empty] | 211 - | 0
212 | [5 empty] | 212 - | 0
213 | [5 empty] | 213 - | 0
214 | [5 empty] | 214 - | 0
215 | [5 empty] | 215 - | 0
216 | [5 empty] | 216 - | 0
217 | [5 empty] | 217 - | 0
218 | [5 empty] | 218 - | 0
219 | [5 empty] | 219 - | 0
220 | [5 empty] | 220 - | 0
221 | [5 empty] | 221 - | 0
222 | [5 empty] | 222 - | 0
223 | [5 empty] | 223 - | 0
224 | [5 empty] | 224 - | 0
225 | [5 empty] | 225 - | 0
226 | [5 empty] | 226 - | 0
227 | [5 empty] | 227 - | 0
228 | [5 empty] | 228 - | 0
229 | [5 empty] | 229 - | 0
230 | [5 empty] | 230 - | 0
231 | [5 empty] | 231 - | 0
232 | [5 empty] | 232 - | 0
233 | [5 empty] | 233 - | 0
234 | [5 empty] | 234 - | 0
235 | [5 empty] | 235 - | 0
236 | [5 empty] | 236 - | 0
237 | [5 empty] | 237 - | 0
238 | [5 empty] | 238 - | 0
239 | [5 empty] | 239 - | 0
240 | [5 empty] | 240 - | 0
241 | [5 empty] | 241 - | 0
242 | [5 empty] | 242 - | 0
243 | [5 empty] | 243 - | 0
244 | [5 empty] | 244 - | 0
245 | [5 empty] | 245 - | 0
246 | [5 empty] | 246 - | 0
247 | [5 empty] | 247 - | 0
248 | [5 empty] | 248 - | 0
249 | [5 empty] | 249 - | 0
250 | [5 empty] | 250 - | 0
251 | [5 empty] | 251 - | 0
252 | [5 empty] | 252 - | 0
253 | [5 empty] | 253 - | 0
254 | [5 empty] | 254 - | 0
255 | [5 empty] | 255 - | 0
256 | [5 empty] | 256 - | 0
257 | [5 empty] | 257 - | 0
258 | [5 empty] | 258 - | 0
259 | [5 empty] | 259 - | 0
260 | [5 empty] | 260 - | 0
261 | [5 empty] | 261 - | 0
262 | [5 empty] | 262 - | 0
263 | [5 empty] | 263 - | 0
264 | [5 empty] | 264 - | 0
265 | [5 empty] | 265 - | 0
266 | [5 empty] | 266 - | 0
267 | [5 empty] | 267 - | 0
268 | [5 empty] | 268 - | 0
269 | [5 empty] | 269 - | 0
270 | [5 empty] | 270 - | 0
271 | [5 empty] | 271 - | 0
272 | [5 empty] | 272 - | 0
273 | [5 empty] | 273 - | 0
274 | [5 empty] | 274 - | 0
275 | [5 empty] | 275 - | 0
276 | [5 empty] | 276 - | 0
277 | [5 empty] | 277 - | 0
278 | [5 empty] | 278 - | 0
279 | [5 empty] | 279 - | 0
280 | [5 empty] | 280 - | 0
281 | [5 empty] | 281 - | 0
282 | [5 empty] | 282 - | 0
283 | [5 empty] | 283 - | 0
284 | [5 empty] | 284 - | 0
285 | [5 empty] | 285 - | 0
286 | [5 empty] | 286 - | 0
287 | [5 empty] | 287 - | 0
288 | [5 empty] | 288 - | 0
289 | [5 empty] | 289 - | 0
290 | [5 empty] | 290 - | 0
291 | [5 empty] | 291 - | 0
292 | [5 empty] | 292 - | 0
293 | [5 empty] | 293 - | 0
294 | [5 empty] | 294 - | 0
295 | [5 empty] | 295 - | 0
296 | [5 empty] | 296 - | 0
297 | [5 empty] | 297 - | 0
298 | [5 empty] | 298 - | 0
299 | [5 empty] | 299 - | 0
300 | [5 empty] | 300 - | 0
Step 1 - Identification
The purpose of this step is to get a listing of all the risks and opportunities that may impact the outcome of the project ... vis a vis the defined project target.
The definition is suggested done via a "post-it" approach where a range of relevant people are "called in" and give input as to which risks and opportunities they see
It is important to note that these should be found holisticly, and hence either look at the full business system ... or use some other base for defining the full risk/pportunity impact of the project
Note - for some issues you may have a risk as well as an opportunity. These have to be entered as two separate entities and unfortunately we have currently no way of linking these (i.e. ensuring that if A happens, B will not happen)
Preliminarily, the project owner may enter the project target to ensure full alignment on this prior to the risk and opportunity identification sessions.
Data collection is "typing up" the input provided, and, in the process, omit duplicates which are different verbalizations on the same risk/opportunity
You may (i.e. you need not) use a grouping if you wish - and you may also decide to "group" later in the process - this is quite optional.
Define/enter
- Decide (potentially) on a grouping. This may be
done AFTER the post-it session
- With an R or an O, whether this is a risk or an
opportunity
- Provide a short (recognizable) name
- Give a verbal description which is accurate/explicit
enough for the project stakeholders to address.
- Assign a named owner to each R/O. This can be
done AFTER the post-it session. Experience shows,
that is important to have a named owner/driver to
ensure action (when two share a responsibility they
tend to have 1% each)
When(ever) you update the AROP model, please remember to update the "update date" here as well.

## 1.a ID Participants
Active Risk & Opportunity Planning3
<Project Name>
Participants | Function
René Redzepi | Project Owner
Gordon Ramsey | Project Leader
Jamie Oliver | Financial Controller
STEP 1.a
ID participants
This step is optional.
Experience has indicated that it may very well be recommendable to "remember" or document the list of people who participated in identifying the risks and opportunities of the project.
Should this be the case, this sheet provide the option of doing so.

## 2.1 Scales
Active Risk & Opportunity Planning3 | [5 empty] | 2.1 - Defining Scales
<Project Name> | [5 empty] | Updated … <date>
Grade | Rationale | Very High | High | Medium | Low | Very Low
Probability/ Likelihood | The very high probability is defined to be below 100% as 100% is a "sure thing" and not a risk anymore. The below scale is found by dividing by 3 to get to a 1% level. | 90% | 30% | 10% | 3% | 1%
… meaning Note: This scale is presumed "fixed" for all projects |  | This will most likely hapen | This may very well happen, something like once in 3 years or in every 3rd project | This may happen, something like once in 10 years or in every 10th project | This is unlikely to happen, something like once in 30 years | This is very unlikely to happen, something like once in 100 years/times, but is cannot be ignored
Financial Impact | Generally baseline for alignment of other scales | 200 | m$
Grade | Very High "Definition" | Very High | High | Medium | Low | Very Low
Financial Impact (m$) | Worst case loss of profits due to … | App. or above 200 | App. 100 | App. 50 | App. 20 | App. or below 20
Downtime / improved uptime | Loss of profits based on operational downtime, calculated as … | => 4 weeks | App 2 weeks | App. 1 week | App 3 days | 2 days or less
Delay / Early ending | Calculated as … |  |  | App or above 6 months | App 3 months | 2 months or less
Qualitative IT impact | Assessed based on … | Severe master data inconsistency | Between VH and M | Systems applied needs significant manual work-around | Between M and VL | Some elements of the IT support is not optimal
Employee Health & Safety | Scale defined/approved by … | Permanent injury above 5% disability or worse | Permanent injury below 5% disability or some 6 months of absenteeism | Approximately 1 month of absenteeism | Approximately 1 week of absenteeism | 2 days of absenteeism or smaller impact
Step 2.1 - Define Scales
The purpose of this step is to get a base/frame of reference upon which the risks and opportunities can be evaluated to ensure aligned evaluation and hence ensure a valid prioritization of risks and opportunitioes and optimal management.
It is fully acknowledged from experience, that this is the most difficult (complex) part of the AROP process (hence the extensive commenting/description)
The definition is suggested done as a simple process between the project manager and the project owner - recommended with the support of the business controller to ensure scale alignment.
The probability/likelihood scale is fixed across all projects, and should NOT be altered.
A scale of financial impact (i.e. EBIT) must be defined, and the Very High can be defined as the full projected impact of the project or when more relavnt - the level of the 1-3 "biggest" risks defined. The remaining (lower) levels are defined by dividing by "approximately two".
If/when the project has other defined benefits, these may be used as scaling parameters - other parameters may also be relevant. It is up to the project management team to decide which scale to use/need. The IMPORTANT issue is, that they are aligned (see the dummy example) hence the involvement of the business controller - "High" must be equally severe irrespective of which scale is applied.
You may chose to copy the calculation rules of the financial benefit to scale the other scales.
When benefits are soft, it is recommended to define a verbal description of the situation of a "very high" "medium", and "very low" impact. Still, do ensure these are aligned with the financial scale to the highest extent possible.
Any given benefit need not be vital to the project, and hence maximum impact need not be "Very High", but may only be "medium" in a particular project.
Process:
Define the scales you need, and overwrite what is in the "grey cells" to match your porject.
The model allows up to five scales, and you are recommended to stay within that frame.
A dummy example - using the data above
In a project we have a specified project objective of 50 m$ over a defined period - but if we do it wrong, the potential loss of earnings is much larger (e.g. 200 m$ as the number above if we e.g. "mess up" master data which causes a lot more negative impact, than the upside we are aiming for). Hence - the larger of the financial benefit and risk of loss is to be used as base for the financial scale (in this case, the 200 m$)
Beyond this, for several of the risks and opportunities it is difficult to define a financial impact. Still - need to prioritize, and we need to do it "right". We already have a finacial scale which is based on the disater of invoking costs of 200 m. The scale steps from Very High to Very Low are "given" by default.
We know (for this dumy project) that a lot of the risks are related to the projected invoking some "operational downtime", where parts of the operation is not working for some time because of this project being in turmoil somewhere. We want a scale of "downtime". The important this is that the scales are aligned, and hence it is recommended to involve a business controller to assess how much downtime would cost us 200 m$. This dummy project is impacting a vital part of the supply chain - so a 4 week downtime would cost 200 m$. Based on this you may rename Scale B to "Downtime" and state above 4 weeks for very high, 2 weeks for high, 1 weeks for medium, 3 days for low, less than 2 days is very low.
Other risks are related to the ability to implement in time, and we also want a scale to cover that. Now, it may be, that the longest delay of implementation you can possibly imagine is 6 months, but that only resembles a financial loss of 40 m$. OK - you may rename scale C to "Delay" and use >6 montsh as medium, 3 months as low (again, ensuring that the scales stay aligned), and then 2 months or less as very low.
Finally - this project applies a new IT system and approach, and to assess these risks, we are using verbal description of the risk impact as numbers does not "work". Thsi is - as the above, carefully aligned in impact.
Now the project operates with independent, but aligned, scales - which should make it easy/easier to assess each risk validly. In other projects Quality, Product Safety impact etc. may be examples of scales relevant to the specific project

## 2.2 Assessment
Active Risk & Opportunity Planning3 | [9 empty] | 2.2 - Assessment
<Project Name> | [9 empty] | Updated … <date>
No. | R/O | Group | Name | Issue/Description | Owner | Step 1 Impact | (Optional/supporting) Impact rationale | Step 2 Probability | (Optional/supporting) Probability rationale | Priority | Gross Map Cell | Gross Severity
[6 empty] | M | This is due to … | H | The 30% is based on … | 0 | 0 | 0
102 | R | Group B | Name 2 | Issue 2 | Person B | VH |  | L |  | -1 | -20 | -7.5
103 | R | Group B | Name 3 | Issue 3 | Person C | L |  | VL |  | -4 | -22 | -0.2
104 | O | Group B | Name 4 | Issue 4 | Person A | M |  | L |  | 3 | 18 | 1.5
105 | R | Group B | Name 5 | Issue 5 | Person C | H |  | L |  | -2 | -19 | -3
106 | O | Group A | Name 6 | Issue 6 | Person A | VL |  | L |  | 4 | 16 | 0.225
107 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
108 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
109 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
110 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
111 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
112 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
113 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
114 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
115 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
116 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
117 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
118 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
119 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
120 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
121 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
122 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
123 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
124 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
125 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
126 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
127 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
128 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
129 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
130 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
131 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
132 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
133 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
134 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
135 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
136 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
137 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
138 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
139 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
140 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
141 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
142 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
143 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
144 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
145 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
146 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
147 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
149 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
150 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
151 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
152 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
153 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
154 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
155 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
156 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
157 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
158 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
159 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
160 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
161 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
162 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
163 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
164 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
165 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
166 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
167 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
168 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
169 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
170 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
171 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
172 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
173 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
174 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
175 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
176 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
177 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
178 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
179 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
180 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
181 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
182 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
183 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
184 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
185 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
186 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
187 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
188 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
189 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
190 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
191 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
192 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
193 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
194 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
195 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
196 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
197 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
198 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
199 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
200 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
201 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
202 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
203 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
204 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
205 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
206 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
207 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
208 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
209 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
210 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
211 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
212 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
213 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
214 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
215 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
216 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
217 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
218 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
219 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
220 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
221 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
222 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
223 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
224 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
225 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
226 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
227 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
228 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
229 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
230 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
231 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
232 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
233 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
234 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
235 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
236 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
237 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
238 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
239 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
240 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
241 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
242 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
243 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
244 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
245 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
246 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
247 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
248 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
249 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
250 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
251 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
252 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
253 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
254 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
255 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
256 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
257 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
258 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
259 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
260 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
261 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
262 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
263 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
264 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
265 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
266 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
267 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
268 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
269 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
270 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
271 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
272 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
273 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
274 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
275 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
276 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
277 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
278 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
279 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
280 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
281 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
282 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
283 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
284 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
285 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
286 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
287 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
288 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
289 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
290 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
291 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
292 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
293 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
294 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
295 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
296 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
297 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
298 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
299 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
300 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0
Step 2.2 - Risk/Oportunity Assessment
The purpose of this step is to prioritize the defined risks and opportunities based on the scales defined in step 2.1.
The definition is suggested done for each risk/opportunity by asking a numer of relevant people of their best insights, and consolidate this to a shared input. You may, but need not, involve the entire project team in every risk/opportunity, but should have those with speciel insights included.
THIS IS HARD WORK - but essential to the process as prioritization is needed to aoid overmanaging small risks and ignoring large ones.
Assessments are made on the VL (Very Low) ... VH (Very High) scales, and hence you need not define any explicit number to any assessment. It is HIGHLY recommended to first assess and define the impact of any risk/opportunity, and then based on this - evaluate the likelihood of this impact materializing. Experience shows this is the easier and "safer" approach. Some risks/opportunities may have multiple (very different) outcomes and probabilities, which need different approaches ... these may need to be split into multiple separate risks/opportunities.
When you have defined a level it is HIGHLY recommended that you give a verbal rationale as to how/why you arrived at that level. This supports your memory, and enable others to address and potential challenge the assessment.
The prioritization is automatically calculated ... as a negative number if it is a risk, and a positive if it is an opportunity.

## 3 Prioritization
Active Risk & Opportunity Planning3 | [7 empty] | 3 - Gross Prioritization
<Project Name> | [7 empty] | Updated … <date>
VH
Gross Assessment
No. | Group | R/O | Name | Issue/Description | Owner | Impact | Probability | Priority | Sort order
0
102 | Group B | R | Name 2 | Issue 2 | Person B | VH | L | -1 | 1R
101 | Group A | R | Name 1 | Issue 1 | Person A |  |  | 0 | 0R
105 | Group B | R | Name 5 | Issue 5 | Person C | H | L | -2 | 2R
104 | Group B | O | Name 4 | Issue 4 | Person A | M | L | 3 | 3O
106 | Group A | O | Name 6 | Issue 6 | Person A | VL | L | 4 | 4O
103 | Group B | R | Name 3 | Issue 3 | Person C | L | VL | -4 | 4R
107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | x
Step 3 - Prioritization
The purpose of this step is to give an overview of the risks and opportunities in order of priority to enable a focused approach to the subsequent handling of these.
The definition is fully automated based on input already provided, and hence there are NO data to enter into this sheet.
Process:
All you need to do to get the overview is to mark the data table (from cell A5 to cell J206) and press "sort" (the column of "sort order" is defined to provide the prioritized listing).
Add-on option: The table includes a column of grouping, which allows you to include a overruling sorting by defined group, should you wish to use this.
The "Map" sheet provides the overview of how many risks/opportunities are in each cell of the map

## 4 Handling
Active Risk & Opportunity Planning3 |  |  |  |  | 4 - Handling
<Project Name> | [5 empty] | Updated … <date>
Decided/implemented Handling Approaches/Actions
No. | Name | Priority | Owner | Early Warning Indicator (Who does what monitoring to enable timely action | Actions (Who is doing what to minimize risks and/or maximize opportunities) | Timing/ Status/ Cadence
101 | Name 1 |  | Person A | We monitor … on a weekly basis to … | We have established a backup … to … We include … in the planning | 2011-03-04
102 | Name 2 | -1 | Person B | - | We have includes a process where … We have added a control to … | Done
103 | Name 3 | -4 | Person C | Monitor … every 2nd week to … | Define action plan to be invoked if risk materializes. | Update monthly
104 | Name 4 | 3 | Person A
105 | Name 5 | -2 | Person C
106 | Name 6 | 4 | Person A
107 | 0 | 0 | 0
108 | 0 | 0 | 0
109 | 0 | 0 | 0
110 | 0 | 0 | 0
111 | 0 | 0 | 0
112 | 0 | 0 | 0
113 | 0 | 0 | 0
114 | 0 | 0 | 0
115 | 0 | 0 | 0
116 | 0 | 0 | 0
117 | 0 | 0 | 0
118 | 0 | 0 | 0
119 | 0 | 0 | 0
120 | 0 | 0 | 0
121 | 0 | 0 | 0
122 | 0 | 0 | 0
123 | 0 | 0 | 0
124 | 0 | 0 | 0
125 | 0 | 0 | 0
126 | 0 | 0 | 0
127 | 0 | 0 | 0
128 | 0 | 0 | 0
129 | 0 | 0 | 0
130 | 0 | 0 | 0
131 | 0 | 0 | 0
132 | 0 | 0 | 0
133 | 0 | 0 | 0
134 | 0 | 0 | 0
135 | 0 | 0 | 0
136 | 0 | 0 | 0
137 | 0 | 0 | 0
138 | 0 | 0 | 0
139 | 0 | 0 | 0
140 | 0 | 0 | 0
141 | 0 | 0 | 0
142 | 0 | 0 | 0
143 | 0 | 0 | 0
144 | 0 | 0 | 0
145 | 0 | 0 | 0
146 | 0 | 0 | 0
147 | 0 | 0 | 0
148 | 0 | 0 | 0
149 | 0 | 0 | 0
150 | 0 | 0 | 0
151 | 0 | 0 | 0
152 | 0 | 0 | 0
153 | 0 | 0 | 0
154 | 0 | 0 | 0
155 | 0 | 0 | 0
156 | 0 | 0 | 0
157 | 0 | 0 | 0
158 | 0 | 0 | 0
159 | 0 | 0 | 0
160 | 0 | 0 | 0
161 | 0 | 0 | 0
162 | 0 | 0 | 0
163 | 0 | 0 | 0
164 | 0 | 0 | 0
165 | 0 | 0 | 0
166 | 0 | 0 | 0
167 | 0 | 0 | 0
168 | 0 | 0 | 0
169 | 0 | 0 | 0
170 | 0 | 0 | 0
171 | 0 | 0 | 0
172 | 0 | 0 | 0
173 | 0 | 0 | 0
174 | 0 | 0 | 0
175 | 0 | 0 | 0
176 | 0 | 0 | 0
177 | 0 | 0 | 0
178 | 0 | 0 | 0
179 | 0 | 0 | 0
180 | 0 | 0 | 0
181 | 0 | 0 | 0
182 | 0 | 0 | 0
183 | 0 | 0 | 0
184 | 0 | 0 | 0
185 | 0 | 0 | 0
186 | 0 | 0 | 0
187 | 0 | 0 | 0
188 | 0 | 0 | 0
189 | 0 | 0 | 0
190 | 0 | 0 | 0
191 | 0 | 0 | 0
192 | 0 | 0 | 0
193 | 0 | 0 | 0
194 | 0 | 0 | 0
195 | 0 | 0 | 0
196 | 0 | 0 | 0
197 | 0 | 0 | 0
198 | 0 | 0 | 0
199 | 0 | 0 | 0
200 | 0 | 0 | 0
201 | 0 | 0 | 0
202 | 0 | 0 | 0
203 | 0 | 0 | 0
204 | 0 | 0 | 0
205 | 0 | 0 | 0
206 | 0 | 0 | 0
207 | 0 | 0 | 0
208 | 0 | 0 | 0
209 | 0 | 0 | 0
210 | 0 | 0 | 0
211 | 0 | 0 | 0
212 | 0 | 0 | 0
213 | 0 | 0 | 0
214 | 0 | 0 | 0
215 | 0 | 0 | 0
216 | 0 | 0 | 0
217 | 0 | 0 | 0
218 | 0 | 0 | 0
219 | 0 | 0 | 0
220 | 0 | 0 | 0
221 | 0 | 0 | 0
222 | 0 | 0 | 0
223 | 0 | 0 | 0
224 | 0 | 0 | 0
225 | 0 | 0 | 0
226 | 0 | 0 | 0
227 | 0 | 0 | 0
228 | 0 | 0 | 0
229 | 0 | 0 | 0
230 | 0 | 0 | 0
231 | 0 | 0 | 0
232 | 0 | 0 | 0
233 | 0 | 0 | 0
234 | 0 | 0 | 0
235 | 0 | 0 | 0
236 | 0 | 0 | 0
237 | 0 | 0 | 0
238 | 0 | 0 | 0
239 | 0 | 0 | 0
240 | 0 | 0 | 0
241 | 0 | 0 | 0
242 | 0 | 0 | 0
243 | 0 | 0 | 0
244 | 0 | 0 | 0
245 | 0 | 0 | 0
246 | 0 | 0 | 0
247 | 0 | 0 | 0
248 | 0 | 0 | 0
249 | 0 | 0 | 0
250 | 0 | 0 | 0
251 | 0 | 0 | 0
252 | 0 | 0 | 0
253 | 0 | 0 | 0
254 | 0 | 0 | 0
255 | 0 | 0 | 0
256 | 0 | 0 | 0
257 | 0 | 0 | 0
258 | 0 | 0 | 0
259 | 0 | 0 | 0
260 | 0 | 0 | 0
261 | 0 | 0 | 0
262 | 0 | 0 | 0
263 | 0 | 0 | 0
264 | 0 | 0 | 0
265 | 0 | 0 | 0
266 | 0 | 0 | 0
267 | 0 | 0 | 0
268 | 0 | 0 | 0
269 | 0 | 0 | 0
270 | 0 | 0 | 0
271 | 0 | 0 | 0
272 | 0 | 0 | 0
273 | 0 | 0 | 0
274 | 0 | 0 | 0
275 | 0 | 0 | 0
276 | 0 | 0 | 0
277 | 0 | 0 | 0
278 | 0 | 0 | 0
279 | 0 | 0 | 0
280 | 0 | 0 | 0
281 | 0 | 0 | 0
282 | 0 | 0 | 0
283 | 0 | 0 | 0
284 | 0 | 0 | 0
285 | 0 | 0 | 0
286 | 0 | 0 | 0
287 | 0 | 0 | 0
288 | 0 | 0 | 0
289 | 0 | 0 | 0
290 | 0 | 0 | 0
291 | 0 | 0 | 0
292 | 0 | 0 | 0
293 | 0 | 0 | 0
294 | 0 | 0 | 0
295 | 0 | 0 | 0
296 | 0 | 0 | 0
297 | 0 | 0 | 0
298 | 0 | 0 | 0
299 | 0 | 0 | 0
300 | 0 | 0 | 0
Step 4 - Handling
The purpose of this step is to DO something about the risks and opportunities we have now defiend and assessed/prioritized.
The definition is suggested defined between the project manager and whoever is defined to "own" the handling of this particular risk or opportunity. This is entered in the "Identification" sheet
Experience shows, that is important to have a named owner/driver to ensure action (when two share a responsibility they tend to have 1% each)
As one handling, we may (but do not always) have the possibility of measuring an Early Warning indicator, which shows us, that this risk or opportunity is actually materializing (e.g. monitoring the development of the sales plans to see if planned sales exceed or fall behind what was planned originally to enable ongoing addressing of this).
The other handling is "doing" something about the risk/opportunity. Looking at risks, this may be preventive (look for traffic before you cross the road) or reactive (wear a helment to reduce impact, if you fall). Some may be both (ABS brakes both reduces the risk of hitting the car in front of you, and reduce the impact, if you hit it) as described in the "How to..." sheet
Define/enter/document your decided actions as precisely as you can, and adequately for your stakeholders to address and challenge.
A column of timing is included to enable you to define update cadence, timing, status on the actions taken.
This is where the real value of AROP is gathered from.

## 5 Re-assessment
Active Risk & Opportunity Planning3 | [9 empty] | 5 - Re-assessment
<Project Name> | [9 empty] | Updated … <date>
|  |  | Gross Assessment (before handling) |  |  | Decided/Implemented Handling |  |  | Net Assessment (after decided handling)
No. | Name | Impact | Probability | Priority | Owner | Early Warning Indicators | Actions Taken | Impact | Probability | Priority | Net Map Cell | Net Severity
101 | Name 1 |  |  |  | Person A | We monitor … on a weekly basis to … | We have established a backup … to … We include … in the planning | L | L |  | 0 | 0
102 | Name 2 | VH | L | -1 | Person B | - | We have includes a process where … We have added a control to … | VH | L | -1 | -20 | -7.5
103 | Name 3 | L | VL | -4 | Person C | Monitor … every 2nd week to … | Define action plan to be invoked if risk materializes. | L | VL | -4 | -22 | -0.2
104 | Name 4 | M | L | 3 | Person A | 0 | 0 | M | L | 3 | 18 | 1.5
105 | Name 5 | H | L | -2 | Person C | 0 | 0 | H | L | -2 | -19 | -3
106 | Name 6 | VL | L | 4 | Person A | 0 | 0 | VL | L | 4 | 16 | 0.225
107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
151 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
166 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
171 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
205 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
214 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
221 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
238 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
246 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
257 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
258 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
268 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
286 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
297 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Step 5 - Re-assessment
The purpose of this step is to show what we expect the impact of our AROP actions are ... and hence, which net risk exposure and upside potential we choose to proceed with "as is"
The definition is suggested defined between the project manager and the owner/driver of the handling of each risk/opportunity.
You may wish (and it is highly recommended) to have these assessments addressed and challenged by other stakeholders to ensure valididty.
Process
Based on the defined handling measures, assess what do you now think is the impact and the probability of each issue.
If the risk level is still higher than acceptable this is not "good enough", you have to add further handling measures(step 4) to improve this, to a level you can accept.
The new (net) priority is automatically calculated.
Note that the net assessment is by default the same as the gross assessment. When having re-assessed to other values, you simply overwrite the formula in columns "I" and "J"
Note that the aim of AROP is to ...
- Reduce the probability and/or impact of risks
as well as ...
- Increase those of opportunities.

## rsklibSimData (hidden)
0f313110fb3ac5f88399d4631a022cb40¦1¦40952604¦fd766a5036f177971e0cd48c2a57e976 | b68abd8915d4ca5954e705e67ec41138 ÐÏà¡±á>þÿ qÙ5¡¢£*+,´µ¶= > ? Ç È É Q R S Ú Û Ü defîïðwxyz ¡()*²³´< = > Å Æ Ç O P Q Ø!Ù!Ú!b#c#d#ì$í$î$u&v&w&ÿ'((()))+++,,,&.'.(.°/±/²/:1;1<1Ã2Ä2Å2M4N4O4×5ýÿÿÿþÿÿÿþÿÿÿýÿÿÿýÿÿÿýÿÿÿýÿÿÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~Root EntryÿÿÿÿÿÿÿÿpÈ ?ôËþÿÿÿRSKLIB Dataÿÿÿÿÿÿÿÿÿÿÿÿ ñkÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿ89ÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿÿ8888888888888888 88988 88 88 888888888888888888888888888888 88 88 88 88 88!88"88#88$88%88&88'88(88)88*88+88,88-88.88/8808818828838848858868878889:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóô45õ444ö444÷444ø444ù444ú444û444ü444ý444þ444ÿ4444444444444444444444 44544 44 44 444444444444444444444444444444 44 44 44 44 44!44"44#44$44%44&44'44(44)44*44+44,44-44.44/44044144244344456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ ýÿÿÿýÿÿÿ ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ_3M 3M¨a¨a¨aÈÈ¨ùð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 4f9091cd7ad0c43b39d16e0efd29e8aeð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | d9315c57d8eb984c9cc2d5f674930308ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 48f7f1e1f270a2a3259c61171ebb9e15ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | c59635951a8c45dd4154fb6a6e46dad5ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 557feab871af349e1def68fc9753ea44ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | d576e5dcb21f35bd70293d132666d7f0ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ    ýÿÿÿýÿÿÿýÿÿÿ     !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 41c28822f64630584c151a952752a665ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 020ab44ca03a7d327fe18dc41faf6f46ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | a2ecc5ca2d697ab523c877fc23d97c13ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | c950d27f6daea1347c668dc95eea86f6ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 9520971e7b27fbb3b2252104cb2efaa4ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 0232697ba750065240225b1fef9af2b2ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõ56ö55÷55ø55ù55ú55û55ü55ý55þ55ÿ555555555555555555555 55655 55 55 555555555555555555555555555555 55 55 55 55 55!55"55#55$55%55&55'55(55)55*55+55,55-55.55/5505515525535545556789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¤ýÿÿÿýÿÿÿýÿÿÿ¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 4c08d2bbe62e79ed4c95d7ec18de4877ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 019f72f0e20c731ff7303900082c3c4bð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | f2d41ccf0e4abc28519f422a2f1f742eð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | d903809cd1cc57922839e9441ed5bcf3ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 4eed196f64a0d132025130eac6cc0a43ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | cfc1cbb3457dc021aa324f5da0c7969bð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ         !"#$%&'()-ýÿÿÿýÿÿÿýÿÿÿ./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | c668b9b46e400570aa0f71930e1051adð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 2172c6bd72eeb93f6a4471536770d101ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 8b08653c373db8d5d19e7167cc9e87fbð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | c6dae1ef244d8e3a72c1e694f1baf552ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 32471a0431a22176d4d5eab5947bbeaeð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | eaa22bd336e822c242a9bd7980501493ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 200568814d80d71666fdd4dddb864b4fð?ð?ð?ð?ð?ð?ð?  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö67÷66ø66ù66ú66û66ü66ý66þ66ÿ666666666666666666666 66766 66 66 666666666666666666666666666666 66 66 66 66 66!66"66#66$66%66&66'66(66)66*66+66,66-66.66/660661662663664665666789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³·ýÿÿÿýÿÿÿýÿÿÿ¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 052c0474a41b4f9843d3c363e962cd40ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 026d476093961dd843fc36bac8337c91ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 84db48943d3721b3d9174be844e54178ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | b2e99c10e408d4812290118d33edc9d0ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | eec1553a01cfebc20208e0da8ff26767ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 52d2f4f7a147478235dccf4505430bcdð?ð?ð?ð?ð?ð?ð?ð?ð?ð?         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ                                 ! " # $ % & ' ( ) * + , - . / 0 1 2 3 4 5 6 7 8 9 : ; < @ ýÿÿÿýÿÿÿýÿÿÿA B C D E F G H I J K L M N O P Q R S T U V W X Y Z [ \ ] ^ _ ` a b c d e f g h i j k l m n o p q r s t u v w x y z { ¦ } ~   ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 17d6f915372cd8a226ca121748ef845að?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 488ff6f45da7665f5b5a48d9583688b0ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 7007ee85171bf13aa1e82dd929f261f6ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 7d2383c13901223b3ec8bc71f7353452ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | f739db58f17c4f42b941f6e0bd6ef964ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 4692f6ef8371dd91b22a6df3c9987c43ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?                                ¡ ¢ £ ¤ ¥ ¦ § ¨ © ª « ¬ ­ ® ¯ ° ± ² ³ ´ µ ¶ · ¸ ¹ º » ¼ ½ ¾ ¿ À Á Â Ã Ä Å Æ Ç È É Ê Ë Ì Í Î Ï Ð Ñ Ò Ó Ô Õ Ö × Ø Ù Ú Û Ü Ý Þ ß à á â ã ä å æ ç è é ê ë ì í î ï ð ñ ò ó ô õ ö ÷ 78ø 77ù 77ú 77û 77ü 77ý 77þ 77ÿ 777877877877877877877877877877 8778877 877 877 877877877877877877877877877877877877877877877 877 877 877 877 877!877"877#877$877%877&877'877(877)877*877+877,877-877.877/8770877187728773877487758776877789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÊýÿÿÿýÿÿÿýÿÿÿËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 9cc31225df88088dd5771f0d96c216c4ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | f4c483b0ea0f398a535c21b22845aba3ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | a89ecf5906f658b9980eafa915db748eð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 2eaeae608b33cf4fbaacee6d86435988ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 2211e0a395dde1e1fac989deab1c7ed1ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | ddd50bc6dc75d152fe6079ade40ba9f9ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?                                ! " # $ % & ' ( ) * + , - . / 0 1 2 3 4 5 6 7 8 9 : ; < = > ? @ A B C D E F G H I J K L M N O P Q R S T U V W X Y Z [ \ ] ^ _ ` a b c d e f g h i j k l m n o p q r s t u v w x y z { ¦ } ~                                   ¡ ¢ £ ¤ ¥ ¦ § ¨ © ª « ¬ ­ ® ¯ ° ± ² ³ ´ µ ¶ · ¸ ¹ º » ¼ ½ ¾ ¿ À Á Â Ã Ä Å Æ Ç È É Ê Ë Ì Í Î Ï Ð Ñ Ò Ó Ô Õ Ö × Ø Ù Ú Û Ü Ý Þ ß à á â ã ä å æ ç è é ê ë ì í î ï ð ñ ò ó ô õ ö ÷ ø ù ú û ü ý þ ÿ                                  ! " # $ % & ' ( ) * + , - . / 0 1 2 3 4 5 6 7 8 9 : ; < = > ? @ A B C D E F G H I J K L M N O P T ýÿÿÿýÿÿÿýÿÿÿU V W X Y Z [ \ ] ^ _ ` a b c d e f g h i j k l m n o p q r s t u v w x y z { ¦ } ~   ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 7a7b19fbeec13e461fc789475cb202e5ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 2009e17d765f47bc4f70257e89c10613ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | bd4643496da6da6db06d6395be9ad6d2ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | f02880f465e047c58f5bfd8abd28b5dbð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 98a0383b2aa5e24e805949182cb1d0a0ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 1c6d56a97990997f1f9843b24e848963ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | bb851787ab653d385e6720ae33d55fbað?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?                                ¡ ¢ £ ¤ ¥ ¦ § ¨ © ª « ¬ ­ ® ¯ ° ± ² ³ ´ µ ¶ · ¸ ¹ º » ¼ ½ ¾ ¿ À Á Â Ã Ä Å Æ Ç È É Ê Ë Ì Í Î Ï Ð Ñ Ò Ó Ô Õ Ö × Ø Ù Ú Û Ü Ý Þ ß à á â ã ä å æ ç è é ê ë ì í î ï ð ñ ò ó ô õ ö 67÷ 66ø 66ù 66ú 66û 66ü 66ý 66þ 66ÿ 666 66 66 66 66 66 66 66 66 66 667 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66 66! 66" 66# 66$ 66% 66& 66' 66( 66) 66* 66+ 66, 66- 66. 66/ 660 661 662 663 664 665 666 7 8 9 : ; < = > ? @ A B C D E F G H I J K L M N O P Q R S T U V W X Y Z [ \ ] ^ _ ` a b c d e f g h i j k l m n o p q r s t u v w x y z { ¦ } ~                                   ¡ ¢ £ ¤ ¥ ¦ § ¨ © ª « ¬ ­ ® ¯ ° ± ² ³ ´ µ ¶ · ¸ ¹ º » ¼ ½ ¾ ¿ À Á Â Ã Ä Å Æ Ç È É Ê Ë Ì Í Î Ï Ð Ñ Ò Ó Ô Õ Ö × Ø Ù Ý ýÿÿÿýÿÿÿýÿÿÿÞ ß à á â ã ä å æ ç è é ê ë ì í î ï ð ñ ò ó ô õ ö ÷ ø ù ú û ü ý þ ÿ ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 9f4fd7619f7b955065d8fa738a4ab71eð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 74eeafd7fd5c9cc7d71eb3595e3c4eaeð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | d65026a1a1b74c5cffe4e7e46025b947ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | f924319b281b0ef0d5d7527e4647eaa2ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | cf9fa4ef843f4b91351aef306e880771ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | ba225116c813769963256c5cbb21ee76ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcgýÿÿÿýÿÿÿýÿÿÿhijklmnopqrstuvwxyz{¦}~ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 015fd90fde5fe19ef48d548d93ee4cbcð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | f1608452608f8588efd90bd081891ac1ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | e5710954716d48688ec54fb0d85879ecð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | e53545ddd3c6c2bd732c86380616aa46ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 79eca5b242a513c2f2231fbf17201cd4ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | d4064c2d3934487f31bedab19b00c05fð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷78ø77ù77ú77û77ü77ý77þ77ÿ777777777777777777777 77877 77 77 777777777777777777777777777777 77 77 77 77 77!77"77#77$77%77&77'77(77)77*77+77,77-77.77/77077177277377477577677789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíñýÿÿÿýÿÿÿýÿÿÿòóôõö÷øùúûüýþÿð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 962754e57d2e1a7ee4fa1721293dcd3fð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | e318fa0a94fc1be6bbb5034b34e6ccdeð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 63f204fd56ebecc925abc3d32df9a3b8ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | c86470288e92d8f008bb29d8aed37ce9ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 612b56eefc758ac8673f451e681949d6ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 902d727d3610901cd53c68d199c26dbcð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuv{ýÿÿÿýÿÿÿýÿÿÿýÿÿÿ¦}~ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 3231e85732616648a346431e2975c066ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 1bbe383732e90e4d4ce82403075b611cð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | a2734824449ada46387388d25c6a10d9ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 520d664bee90593c41043ad6a3ae545cð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | 00ee0394257577c3c1fa4f07a42d5263ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | ba660020e41ac7a121954fa2bebc6bb2ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð? | b1a3ae6ac533e301c7ac4cfa055ab03cð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?ð?  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷ø89ù88ú88û88ü88ý88þ88ÿ888888888888888888888 88988 88 88 888888888888888888888888888888 88 88 88 88 88!88"88#88$88%88&88'88(88)88*88+88,88-88.88/8808818828838848858868878889:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿýÿÿÿýÿÿÿýÿÿÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | dc38ea80729c90aae5398390e40829fc  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ ýÿÿÿýÿÿÿýÿÿÿ ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f7635410bdbc63f3b6df6a29850ec09b9:99999999999999999999999999999999999999999999 99:99 99 99 999999999999999999999999999999 99 99 99 99 99!99"99#99$99%99&99'99(99)99*99+99,99-99.99/990991992993994995996997998999:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõ5ö÷øùúûüýþÿ 5   ýÿÿÿýÿÿÿýÿÿÿ     !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | fd5fd72705de6d831d2e3a0c2298a960  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ ¢ýÿÿÿýÿÿÿýÿÿÿ£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | b249c2b01c23a6751e0963b1ae1f276b89888888888888888888888888888888888888888888888888 88988 88 88 888888888888888888888888888888 88 88 88 88 88!88"88#88$88%88&88'88(88)88*88+88,88-88.88/8808818828838848858868878889:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóô()õ((ö((÷((ø((ù((ú((û((ü((ý((þ((ÿ((((((((((((((((((((( (()(( (( (( (((((((((((((((((((((((((((((( (( (( (( (( ((!(("((#(($((%((&(('((+((ýÿÿÿýÿÿÿýÿÿÿ,((-((.((/((0((1((2((3((456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~ | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | 879b5e7b9a8663ebee4434e5d5aa9048  ¡¢£¤¥¦§¨©ª«¬­®¯°±²³´µ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ         !"#$%&'()*+,-./0123456789:;<=>?@ABCDEFGHIJKLMNOPQRSTUVWXYZ[\]^_`abcdefghijklmnopqrstuvwxyz{¦}~  ¡¢£¤¥¦§¨©ª«¬­®¯°±µýÿÿÿýÿÿÿýÿÿÿ¶·¸¹º»¼½¾¿ÀÁÂÃÄÅÆÇÈÉÊËÌÍÎÏÐÑÒÓÔÕÖ×ØÙÚÛÜÝÞßàáâãäåæçèéêëìíîïðñòóôõö÷øùúûüýþÿ  | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | b5cccb99b7a95aebfc238b030ec63bbf9:9999999999999999999999999999 99 99 99 99 99 99 99 99 99: 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99 99! 99" 99# 99$ 99% 99& 99' 99( 99) 99* 99+ 99, 99- 99. 99/ 990 991 992 993 994 995 996 997 998 999 : ; < = > ? @ A B C D E F G H I J K L M N O P Q R S T U V W X Y Z [ \ ] ^ _ ` a b c d e f g h i j k l m n o p q r s t u v w x y z { ¦ } ~                                   ¡ ¢ £ ¤ ¥ ¦ § ¨ © ª « ¬ ­ ® ¯ ° ± ² ³ ´ µ ¶ · ¸ ¹ º » ¼ ½ ¾ ¿ À Á Â Ã Ä Å Æ Ç È É Ê Ë Ì Í Î Ï Ð Ñ Ò Ó Ô Õ Ö × Ø Ù Ú Û Ü Ý Þ ß à á â ã ä å æ ç è é ê ë ì í î ï ð ñ ò ó ô õ 56ö 55÷ 55ø 55ù 55ú 55û 55ü 55ý 55þ 55ÿ 555 55 55 55 55 55 55 55 55 55 556 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55 55! 55" 55# 55$ 55% 55& 55' 55( 55) 55* 55+ 55, 55- 55. 55/ 550 551 552 553 554 555 6 7 8 9 : ; ? ýÿÿÿýÿÿÿýÿÿÿ@ A B C D E F G H I J K L M N O P Q R S T U V W X Y Z [ \ ] ^ _ ` a b c d e f g h i j k l m n o p q r s t u v w x y z { ¦ } ~    | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9 | f91704691ca1a13d411d1dcdd440a4d9